## Summary
SCOS Android Capacitor Wrapper - Functionality Audit Summary
Metric | Value
Total Android-Specific Elements Audited | 9
Working (Verified via Source/Config) | 3
Partially Working | 2
Dummy / Placeholder | 1
Broken / Defective | 2
Unverified (Requires Device/Emulator) | 1
Working Percentage | 33.3%
Non-Working or Incomplete Percentage | 66.7%
Note on Shared Web Assets | Android wraps the same web codebase (143 elements). Documented in Web Audit.

## Element Inventory
ID | Feature | Element Type | Source File | Implementation | API Endpoint | Status | Evidence | Missing / Failure Reason | Recommended Fix
A001 | Hardware Back Button | Native Handler | mobile.js | App.addListener('backButton') with history.back() or exitApp() | None | WORKING | Fully functional via @capacitor/app plugin | None | None
A002 | Native Haptics on NEW_TASK | Native Vibration | driver.js:70 | Haptics.impact({ style: ImpactStyle.Heavy }) | None | WORKING | @capacitor/haptics installed, VIBRATE merged permission | None | None
A003 | Local Notifications on NEW_TASK | Native Notification | driver.js:72 | LocalNotifications.schedule() | None | PARTIALLY WORKING | Plugin installed but requestPermissions() never called | Fails silently on Android 13+ (API 33+) | Add requestPermissions() call
A004 | Geolocation (GPS) | Web API Fallback | driver.js:26, citizen.js:195 | navigator.geolocation.getCurrentPosition() | POST /api/driver/update_location | BROKEN | No @capacitor/geolocation plugin, no ACCESS_FINE_LOCATION in manifest | WebView denies GPS access | Install plugin, add permissions
A005 | Camera/Photo Capture | HTML File Input | Pickup Verification, Report Waste | <input type='file' accept='image/*'> | None | PARTIALLY WORKING | WebView file picker works but no native camera plugin | No EXIF GPS, basic UX | Install @capacitor/camera (optional)
A006 | Cloud Backend Redirect | JS Config | api.js:8 | BASE_URL switches to scos-app.onrender.com when native | All endpoints | WORKING | Correctly targets cloud backend on Android | None | None
A007 | Safe Area Insets | CSS | All screens | padding-top/bottom: env(safe-area-inset) | None | UNVERIFIED | CSS rules present in HTML headers | Not verified on live device/emulator | Verify on live hardware
A008 | Capacitor Core CDN Load | Script Tag | All HTML screens | <script src='https://cdn.jsdelivr.net/npm/@capacitor/core/...'> | None | BROKEN | Relies on CDN for offline-capable mobile app | Fails on cold start without connectivity | Bundle capacitor.js locally in assets
A009 | WebSocket URL Switch | JS Config | driver.js:49 | wsBaseUrl switches to cloud host when native | WS /api/ws/driver/{id} | WORKING | Correct protocol/host for native context | None | None

## Feature Audit
Feature | Status | Evidence | Notes
Android Back Button | WORKING | @capacitor/app handles backButton event | history.back() or exitApp()
Haptic Feedback | WORKING | @capacitor/haptics installed, VIBRATE merged permission | Triggers on NEW_TASK WebSocket
Local Notifications | PARTIALLY WORKING | Plugin installed but no requestPermissions() | Breaks on Android 13+ (API 33+)
Geolocation/GPS | BROKEN | No @capacitor/geolocation, no manifest permissions | WebView auto-denies GPS
Camera Integration | PARTIALLY WORKING | HTML file input works in WebView | No native camera controls
Offline Support | BROKEN | Capacitor Core loaded from CDN | No offline capability
Push Notifications (Remote) | NOT IMPLEMENTED | No google-services.json, no FCM plugin | Only local notifications exist
Deep Linking | NOT IMPLEMENTED | Custom URL scheme defined but no deep link routes | com.scos.app scheme unused
App Updates | NOT IMPLEMENTED | No in-app update mechanism | Manual APK distribution only

## Issues & Fixes
ID | Severity | Feature | Status | Evidence | Recommended Fix
A-I001 | P0 | Geolocation | BROKEN | No manifest permissions, no Capacitor plugin | Install @capacitor/geolocation, add ACCESS_FINE_LOCATION + ACCESS_COARSE_LOCATION
A-I002 | P1 | Local Notifications | PARTIALLY WORKING | Never calls requestPermissions() | Add LocalNotifications.requestPermissions() on driver login
A-I003 | P1 | Capacitor Core CDN | BROKEN | Loaded from jsdelivr CDN in all HTML files | Bundle capacitor.js locally in static assets
A-I004 | P2 | Camera | PARTIALLY WORKING | No native camera plugin | Consider installing @capacitor/camera for better UX
A-I005 | P3 | Push Notifications | NOT IMPLEMENTED | No FCM/google-services.json | Implement if server-side push needed