## Summary
SCOS Web Platform Functionality Audit Summary
Metric | Value
Total Interactive Elements Audited | 143
Working (Verified) | 61
Partially Working | 12
Dummy / Placeholder | 42
Broken / Defective | 19
Unverified | 9
Working Percentage | 42.7%
Non-Working or Incomplete Percentage | 57.3%
Total Screens Audited | 18
Total Backend API Endpoints Inspected | 22
Verification Method | Static Code Trace & Local Runtime Validation

## Element Inventory
ID | Role | Screen | Element Label | Element Type | Source File | Line | Intended Behavior | Actual Implementation | API Endpoint | Persists Data | Status | Evidence | Missing/Failure Reason | Recommended Fix
W001 | All | Login Screen | Email Input | Text Input | Login Screen/index.html | 222 | Accept user email | Reads value on form submit | POST /api/auth/login | No | WORKING | Value sent as username field in FormData | None | None
W002 | All | Login Screen | Password Input | Password Input | Login Screen/index.html | 227 | Accept user password | Reads value on form submit | POST /api/auth/login | No | WORKING | Value sent as password field in FormData | None | None
W003 | All | Login Screen | Login Submit Button | Submit Button | Login Screen/index.html | 243 | Submit login credentials | Triggers form submit, calls API.loginUser | POST /api/auth/login | No (reads) | WORKING | Stores token, role, user_id in localStorage | None | None
W004 | All | Login Screen | Login Form | Form | Login Screen/index.html | 219 | Container for login submission | submit event in auth.js:15-47 | POST /api/auth/login | No | WORKING | Full login flow with error handling | None | None
W005 | All | Login Screen | Role Selector - Citizen | Button | Login Screen/index.html | 186 | Select citizen role | Toggles CSS classes only | None | No | DUMMY / PLACEHOLDER | Visual toggle only; role comes from backend | Role ignored by auth logic | None needed - cosmetic
W006 | All | Login Screen | Role Selector - Driver | Button | Login Screen/index.html | 190 | Select driver role | Toggles CSS classes only | None | No | DUMMY / PLACEHOLDER | Visual toggle only | Role ignored by auth logic | None needed - cosmetic
W007 | All | Login Screen | Role Selector - Admin | Button | Login Screen/index.html | 194 | Select admin role | Toggles CSS classes only | None | No | DUMMY / PLACEHOLDER | Visual toggle only | Role ignored by auth logic | None needed - cosmetic
W008 | All | Login Screen | Password Visibility Toggle | Button | Login Screen/index.html | 229 | Toggle password visibility | No event handler attached | None | No | DUMMY / PLACEHOLDER | Button exists but has no onclick listener | Does not reveal/conceal password | Add toggle handler
W009 | All | Login Screen | Remember Me Checkbox | Checkbox | Login Screen/index.html | 234 | Remember user session | Visual-only, not read by auth.js | None | No | DUMMY / PLACEHOLDER | Neither read nor stored in localStorage | Ignored completely | Implement or remove
W010 | All | Login Screen | Forgot Password Link | Link | Login Screen/index.html | 241 | Navigate to password reset | href='#' with no handler | None | No | DUMMY / PLACEHOLDER | Dead anchor link | No password reset feature | Implement or remove
W011 | All | Login Screen | Google Social Login | Button | Login Screen/index.html | 256 | Login via Google OAuth | No event handler | None | No | DUMMY / PLACEHOLDER | Completely inert button | No OAuth implemented | Implement or remove
W012 | All | Login Screen | Apple Social Login | Button | Login Screen/index.html | 260 | Login via Apple ID | No event handler | None | No | DUMMY / PLACEHOLDER | Completely inert button | No OAuth implemented | Implement or remove
W013 | All | Login Screen | Register Link | Link | Login Screen/index.html | 269 | Navigate to registration | Standard href navigation | None | No | WORKING | Links to Register Screen/index.html | None | None
W014 | All | Register Screen | Full Name Input | Text Input | Register Screen/index.html | 176 | Accept user full name | Read on form submit in auth.js:53 | POST /api/auth/register | No | WORKING | Sent as 'name' in JSON body | None | None
W015 | All | Register Screen | Email Input | Email Input | Register Screen/index.html | 184 | Accept user email | Read on form submit in auth.js:54 | POST /api/auth/register | No | WORKING | Sent as 'email' in JSON body | None | None
W016 | All | Register Screen | Password Input | Password Input | Register Screen/index.html | 192 | Accept user password | Read on form submit in auth.js:55 | POST /api/auth/register | No | WORKING | Sent as 'password' in JSON body | None | None
W017 | All | Register Screen | Register Form | Form | Register Screen/index.html | 170 | Container for registration | submit event in auth.js:49-78 | POST /api/auth/register | Yes | WORKING | Full registration flow | None | None
W018 | All | Register Screen | Create Account Button | Submit Button | Register Screen/index.html | 235 | Submit registration | Triggers form submission | POST /api/auth/register | Yes | WORKING | Creates user, redirects to Login | None | None
W019 | All | Register Screen | Sign In Link | Link | Register Screen/index.html | 243 | Navigate to login | Standard href navigation | None | No | WORKING | Links to Login Screen | None | None
W020 | All | Register Screen | Role Radio - Citizen | Radio | Register Screen/index.html | 200 | Select citizen role | Visual-only, ignored by auth.js | None | No | DUMMY / PLACEHOLDER | Not read during registration | Role forced to CITIZEN in backend | None needed
W021 | All | Register Screen | Role Radio - Driver | Radio | Register Screen/index.html | 208 | Select driver role | Visual-only, ignored by auth.js | None | No | DUMMY / PLACEHOLDER | Not read during registration | Role forced to CITIZEN | None needed
W022 | All | Register Screen | Role Radio - Admin | Radio | Register Screen/index.html | 216 | Select admin role | Visual-only, ignored by auth.js | None | No | DUMMY / PLACEHOLDER | Not read during registration | Role forced to CITIZEN | None needed
W023 | All | Register Screen | Terms Checkbox | Checkbox | Register Screen/index.html | 228 | Accept terms of service | Not validated by auth.js | None | No | DUMMY / PLACEHOLDER | Registration proceeds without check | No validation enforced | Add validation or remove
W024 | All | Register Screen | Terms of Service Link | Link | Register Screen/index.html | 231 | View terms | href='#' dead link | None | No | DUMMY / PLACEHOLDER | Dead anchor | No terms page | Implement or remove
W025 | All | Register Screen | Privacy Policy Link | Link | Register Screen/index.html | 231 | View privacy policy | href='#' dead link | None | No | DUMMY / PLACEHOLDER | Dead anchor | No privacy page | Implement or remove
W026 | All | Role Selection | Citizen Card | Button | Role Selection/index.html | 149 | Select citizen role | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation or logic | Wire onclick
W027 | All | Role Selection | Driver Card | Button | Role Selection/index.html | 164 | Select driver role | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation or logic | Wire onclick
W028 | All | Role Selection | Admin Card | Button | Role Selection/index.html | 179 | Select admin role | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation or logic | Wire onclick
W029 | All | Role Selection | Contact Support Link | Link | Role Selection/index.html | 198 | Contact support | href='#' dead link | None | No | DUMMY / PLACEHOLDER | Dead anchor | No support page | Remove
W030 | All | Splash Screen | Auto Redirect Timer | Script | Splash Screen/index.html | 206 | Auto-navigate after 3s | setTimeout to Login Screen | None | No | WORKING | Functional 3s timer redirect | None | None
W031 | All | Onboarding 1 | Skip Button | Button | Onboarding 1/index.html | 131 | Skip onboarding | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W032 | All | Onboarding 1 | Next Button | Button | Onboarding 1/index.html | 177 | Go to Onboarding 2 | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W033 | All | Onboarding 2 | Skip Button | Button | Onboarding 2/index.html | 192 | Skip onboarding | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W034 | All | Onboarding 2 | Next Button | Button | Onboarding 2/index.html | 195 | Go to Onboarding 3 | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W035 | All | Onboarding 3 | Skip Button | Button | Onboarding 3/index.html | 134 | Skip onboarding | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W036 | All | Onboarding 3 | Get Started Button | Button | Onboarding 3/index.html | 194 | Enter app | No handler attached | None | No | DUMMY / PLACEHOLDER | Completely inert | No navigation | Wire onclick
W037 | Citizen | Citizen Dashboard | Profile Avatar Logout | Image | Citizen Dashboard/index.html | 130 | Logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional logout | None | None
W038 | Citizen | Citizen Dashboard | Notifications Bell | Button | Citizen Dashboard/index.html | 136 | View notifications | Shows toast only | None | No | DUMMY / PLACEHOLDER | Toast: 'You have no new notifications.' | No notification system | Implement notifications
W039 | Citizen | Citizen Dashboard | Wellness Score Card | Display | Citizen Dashboard/index.html | 144 | Show cleanliness score | Fetches from API, updates DOM | GET /api/citizen/dashboard | No (reads) | WORKING | Live server data calculation | None | None
W040 | Citizen | Citizen Dashboard | EcoPoints Balance | Display | Citizen Dashboard/index.html | 167 | Show points balance | Reads localStorage | None | No (reads) | WORKING | Synced from dashboard API | None | None
W041 | Citizen | Citizen Dashboard | Redeem Rewards Button | Button | Citizen Dashboard/index.html | 179 | Navigate to rewards | Redirects to Rewards screen | None | No | WORKING | Functional navigation | None | None
W042 | Citizen | Citizen Dashboard | View All Reports Link | Button | Citizen Dashboard/index.html | 189 | View complaint history | Inline onclick navigation | None | No | WORKING | Navigates to Complaint History | None | None
W043 | Citizen | Citizen Dashboard | Recent Report Cards | Dynamic Cards | Citizen Dashboard/index.html | 193 | Show top 2 complaints | Fetches from API, renders cards | GET /api/citizen/my_reports | No (reads) | PARTIALLY WORKING | Data is real but cards are not clickable | No detail drilldown modal | Add click handler for details
W044 | Citizen | Citizen Dashboard | Explore Nearby Bins | Button | Citizen Dashboard/index.html | 204 | View bin map | Onclick navigates to Cleanliness Heatmap | None | No | BROKEN | Target screen has Admin auth guard | Citizen gets kicked to Login | Change target or fix auth guard
W045 | Citizen | Citizen Dashboard | Report Waste FAB | FAB | Citizen Dashboard/index.html | 213 | Submit new report | Redirects to Report Waste | None | No | WORKING | Functional navigation | None | None
W046 | Citizen | Citizen Dashboard | Bottom Nav Home | Link | Citizen Dashboard/index.html | 220 | Navigate home | citizen.js nav router | None | No | WORKING | Routes to Citizen Dashboard | None | None
W047 | Citizen | Citizen Dashboard | Bottom Nav Map | Link | Citizen Dashboard/index.html | 225 | View map | citizen.js nav router | None | No | BROKEN | Target Waste Heatmap has Admin auth guard | Citizen gets kicked to Login | Fix routing or auth
W048 | Citizen | Citizen Dashboard | Bottom Nav Tasks | Link | Citizen Dashboard/index.html | 230 | View tasks/complaints | citizen.js nav router | None | No | WORKING | Routes to Complaint History | None | None
W049 | Citizen | Citizen Dashboard | Bottom Nav Reports | Link | Citizen Dashboard/index.html | 235 | Submit report | citizen.js nav router | None | No | WORKING | Routes to Report Waste | None | None
W050 | Citizen | Citizen Dashboard | Bottom Nav Stats | Link | Citizen Dashboard/index.html | 240 | View stats | citizen.js nav router | None | No | BROKEN | Target Cleanliness Heatmap has Admin guard | Citizen gets kicked to Login | Fix routing or auth
W051 | Citizen | Report Waste | Back Arrow Icon | Span | Report Waste/index.html | 131 | Navigate back | Not wrapped in button/a tag | None | No | BROKEN | citizen.js queries 'header button, header a' - span ignored | Cannot navigate back | Wrap in button
W052 | Citizen | Report Waste | Profile Avatar Logout | Image | Report Waste/index.html | 136 | Logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional logout | None | None
W053 | Citizen | Report Waste | Report Form | Form | Report Waste/index.html | 147 | Submit waste report | submit event in citizen.js:210-271 | POST /api/citizen/report_issue | Yes | WORKING | Full JSON submission with validation | None | None
W054 | Citizen | Report Waste | Image Upload Dropzone | File Input | Report Waste/index.html | 150 | Upload waste photo | Opens file picker but image not sent | None | No | PARTIALLY WORKING | File picker works but image discarded on submit | Image never uploaded to backend | Include in API payload
W055 | Citizen | Report Waste | Refine GPS Button | Button | Report Waste/index.html | 169 | Refine GPS coordinates | No handler attached | None | No | DUMMY / PLACEHOLDER | Static display coordinates | Button does nothing | Implement geolocation refresh
W056 | Citizen | Report Waste | Zone Dropdown | Select | Report Waste/index.html | 175 | Select ward/zone | Read on submit citizen.js:221 | POST /api/citizen/report_issue | No | WORKING | Options: Ward 12, 15, 22 | None | None
W057 | Citizen | Report Waste | Area Input | Text Input | Report Waste/index.html | 189 | Enter locality | Read and validated on submit | POST /api/citizen/report_issue | No | WORKING | Required field with error toast | None | None
W058 | Citizen | Report Waste | Waste Type General | Radio | Report Waste/index.html | 195 | Select waste type | Read on submit citizen.js:232 | POST /api/citizen/report_issue | No | WORKING | Default selected category | None | None
W059 | Citizen | Report Waste | Waste Type Plastic | Radio | Report Waste/index.html | 202 | Select waste type | Read on submit citizen.js:232 | POST /api/citizen/report_issue | No | WORKING | Plastic category option | None | None
W060 | Citizen | Report Waste | Waste Type Hazardous | Radio | Report Waste/index.html | 209 | Select waste type | Read on submit citizen.js:232 | POST /api/citizen/report_issue | No | WORKING | Hazardous category option | None | None
W061 | Citizen | Report Waste | Description Textarea | Textarea | Report Waste/index.html | 220 | Describe issue | No id/name, not read by citizen.js | None | No | DUMMY / PLACEHOLDER | Text is completely discarded | Orphaned form field | Add id and include in submission
W062 | Citizen | Report Waste | Submit Report Button | Submit Button | Report Waste/index.html | 225 | Submit waste report | Triggers form submit | POST /api/citizen/report_issue | Yes | WORKING | Submits data, awards +10 pts, redirects | None | None
W063 | Citizen | Report Waste | Notifications Icon | Span | Report Waste/index.html | 135 | View notifications | No handler | None | No | DUMMY / PLACEHOLDER | Raw span with hover only | Not clickable | None needed
W064 | Citizen | Complaint History | Profile Avatar Logout | Image | Complaint History/index.html | 131 | Logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional logout | None | None
W065 | Citizen | Complaint History | Notifications Button | Button | Complaint History/index.html | 136 | View notifications | No handler (lacks id) | None | No | BROKEN | Click does nothing | Missing btn-notifications id | Add id or handler
W066 | Citizen | Complaint History | Complaints List | Dynamic Container | Complaint History/index.html | 148 | Show all complaints | loadComplaints() renders full list | GET /api/citizen/my_reports | No (reads) | PARTIALLY WORKING | Data is real but cards not clickable | No detail drilldown | Add click handler
W067 | Citizen | Complaint History | Add Report FAB | FAB | Complaint History/index.html | 157 | Submit new report | Redirects to Report Waste | None | No | WORKING | Functional navigation | None | None
W068 | Citizen | Rewards | Profile Avatar Logout | Image | Rewards/index.html | 98 | Logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional logout | None | None
W069 | Citizen | Rewards | Notifications Button | Button | Rewards/index.html | 104 | View notifications | No handler | None | No | BROKEN | Click does nothing | Unwired button | Add handler
W070 | Citizen | Rewards | EcoPoints Display | Display | Rewards/index.html | 117 | Show points balance | updatePointsUI in citizen.js | None | No (reads) | WORKING | Live synced from localStorage | None | None
W071 | Citizen | Rewards | Tier Progress Bar | Display Card | Rewards/index.html | 122 | Show tier progress | Static hardcoded (82%, 260 pts) | None | No | DUMMY / PLACEHOLDER | Static mockup data | Not dynamic | Implement tier logic
W072 | Citizen | Rewards | Impact Stats Cards | Display Cards | Rewards/index.html | 137 | Show environmental impact | Static hardcoded (42.5 kg CO2) | None | No | DUMMY / PLACEHOLDER | Static mockup metrics | Not calculated | Implement tracking
W073 | Citizen | Rewards | View All Rewards | Button | Rewards/index.html | 164 | View all rewards | No handler | None | No | DUMMY / PLACEHOLDER | Visual placeholder | Does nothing | Implement or remove
W074 | Citizen | Rewards | Dynamic Redeem Buttons | Buttons | citizen.js:304 | Redeem reward | onclick calls redeemReward() | POST /api/citizen/redeem_reward | Yes | PARTIALLY WORKING | API works but toast.js missing in Rewards page | ReferenceError on showToast | Add toast.js import
W075 | Citizen | Rewards | District Leaderboard | Cards | Rewards/index.html | 245 | Show rankings | Static hardcoded names/scores | None | No | DUMMY / PLACEHOLDER | Hardcoded ranking mockup | Not dynamic | Implement leaderboard API
W076 | Citizen | Rewards | View Full Leaderboard | Button | Rewards/index.html | 302 | View leaderboard | No handler | None | No | DUMMY / PLACEHOLDER | Visual placeholder | Does nothing | Implement or remove
W077 | Admin | Waste Heatmap | Profile Avatar Logout | Image | Waste Heatmap/index.html | 135 | Admin logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional admin logout | None | None
W078 | Admin | Waste Heatmap | Notifications Bell | Button | Waste Heatmap/index.html | 141 | View alerts | Toast only via admin.js:61 | None | No | DUMMY / PLACEHOLDER | Toast: 'No critical system alerts.' | No alert system | Implement alerts
W079 | Admin | Waste Heatmap | By Ward Toggle | Button | Waste Heatmap/index.html | 156 | Filter by ward | Toggles CSS, shows toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Switched view to By Ward' | No re-query | Implement filter
W080 | Admin | Waste Heatmap | By Waste Type Toggle | Button | Waste Heatmap/index.html | 157 | Filter by type | Toggles CSS, shows toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Switched view to By Waste Type' | No re-query | Implement filter
W081 | Admin | Waste Heatmap | District Filter Chip | Chip | Waste Heatmap/index.html | 160 | Filter by district | Toast only via admin.js:19 | None | No | DUMMY / PLACEHOLDER | Toast: 'Filter options opened' | No dropdown | Implement dropdown
W082 | Admin | Waste Heatmap | Type Filter Chip | Chip | Waste Heatmap/index.html | 164 | Filter by waste type | Toast only via admin.js:19 | None | No | DUMMY / PLACEHOLDER | Toast: 'Filter options opened' | No dropdown | Implement dropdown
W083 | Admin | Waste Heatmap | Live Insights Stats | Display | Waste Heatmap/index.html | 197 | Show admin KPIs | Fetches from API, updates DOM | GET /api/admin/overview | No (reads) | WORKING | Live server data with formula | None | None
W084 | Admin | Waste Heatmap | Assign Driver Buttons | Dynamic Buttons | admin.js:248 | Assign driver to complaint | Opens assign modal with complaint data | GET /api/admin/complaints | No | WORKING | Opens pre-populated modal | None | None
W085 | Admin | Waste Heatmap | Driver Select Dropdown | Select | Waste Heatmap/index.html | 245 | Select driver for assignment | Populated with drivers from API | GET /api/admin/drivers | No | WORKING | Live driver list | None | None
W086 | Admin | Waste Heatmap | Modal Cancel Button | Button | Waste Heatmap/index.html | 249 | Cancel assignment | Hides modal | None | No | WORKING | Functional modal dismiss | None | None
W087 | Admin | Waste Heatmap | Modal Confirm Assign | Button | Waste Heatmap/index.html | 253 | Confirm driver assignment | Calls API.assignTask, refreshes list | POST /api/admin/assign_task | Yes | WORKING | Full-stack write operation | None | None
W088 | Admin | Waste Heatmap | Nav Home | Link | Waste Heatmap/index.html | 264 | Navigate home | admin.js nav router | None | No | WORKING | Routes to Waste Heatmap | None | None
W089 | Admin | Waste Heatmap | Nav Map | Link | Waste Heatmap/index.html | 269 | View map | admin.js nav router | None | No | WORKING | Routes to Waste Heatmap | None | None
W090 | Admin | Waste Heatmap | Nav Tasks | Link | Waste Heatmap/index.html | 274 | View tasks | admin.js nav router | None | No | WORKING | Routes to Illegal Dumping | None | None
W091 | Admin | Waste Heatmap | Nav Reports | Link | Waste Heatmap/index.html | 279 | View reports | admin.js nav router | None | No | WORKING | Routes to Cleanliness Heatmap | None | None
W092 | Admin | Waste Heatmap | Nav Stats | Link | Waste Heatmap/index.html | 284 | View stats | Toast only | None | No | DUMMY / PLACEHOLDER | Toast: 'Stats view loading...' | No stats page | Implement stats
W093 | Admin | Illegal Dumping | Profile Avatar Logout | Image | Illegal Dumping/index.html | 130 | Admin logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional admin logout | None | None
W094 | Admin | Illegal Dumping | Notifications Bell | Button | Illegal Dumping/index.html | 136 | View alerts | Toast only | None | No | DUMMY / PLACEHOLDER | Toast: 'No critical system alerts.' | None | None
W095 | Admin | Illegal Dumping | Critical Map Marker | Div | Illegal Dumping/index.html | 149 | Show hotspot | CSS hover only, no click | None | No | DUMMY / PLACEHOLDER | Visual marker, no interaction | Not clickable | Add click handler
W096 | Admin | Illegal Dumping | Moderate Map Marker | Div | Illegal Dumping/index.html | 158 | Show hotspot | CSS hover only, no click | None | No | DUMMY / PLACEHOLDER | Visual marker | Not clickable | Add click handler
W097 | Admin | Illegal Dumping | Clustered Marker | Div | Illegal Dumping/index.html | 164 | Show cluster | Static badge, no click | None | No | DUMMY / PLACEHOLDER | Visual marker | Not clickable | Add click handler
W098 | Admin | Illegal Dumping | Live Incidents Panel | Display | Illegal Dumping/index.html | 174 | Show incident stats | Fetches from API | GET /api/admin/illegal_dumping | No (reads) | WORKING | Live server data for admins | None | None
W099 | Admin | Illegal Dumping | AI Prediction Card | Display | Illegal Dumping/index.html | 204 | Show AI prediction | Static hardcoded | None | No | DUMMY / PLACEHOLDER | Static 'Private Contractors' 85% confidence | Not dynamic | Implement AI feed
W100 | Admin | Illegal Dumping | Weekly Chart | Display | Illegal Dumping/index.html | 225 | Show frequency chart | Static HTML bars | None | No | DUMMY / PLACEHOLDER | Static bar chart mockup | Not dynamic | Implement chart data
W101 | Admin | Illegal Dumping | Dispatch Team Button | Button | Illegal Dumping/index.html | 249 | Dispatch response team | admin.js handler checks 'Dispatch Team' but button says 'Dispatching Team' | None | No | BROKEN | String mismatch causes handler to miss | Button completely unhandled | Fix text or handler match
W102 | Admin | Illegal Dumping | Emergency FAB | Button | Illegal Dumping/index.html | 258 | Emergency alert | No handler | None | No | DUMMY / PLACEHOLDER | Unwired red warning button | Does nothing | Implement or remove
W103 | Admin | Cleanliness Heatmap | Profile Avatar Logout | Image | Cleanliness Heatmap/index.html | 118 | Admin logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional admin logout | None | None
W104 | Admin | Cleanliness Heatmap | Notifications Bell | Button | Cleanliness Heatmap/index.html | 124 | View alerts | Toast only | None | No | DUMMY / PLACEHOLDER | Toast: 'No critical system alerts.' | None | None
W105 | Admin | Cleanliness Heatmap | Bin Markers (3) | Divs | Cleanliness Heatmap/index.html | 140 | Show bin locations | CSS hover tooltips only | None | No | DUMMY / PLACEHOLDER | Tooltip-only markers | Not clickable | Add click handlers
W106 | Admin | Cleanliness Heatmap | Search Input | Text Input | Cleanliness Heatmap/index.html | 175 | Search bins | No handler attached | None | No | DUMMY / PLACEHOLDER | Unwired text input | Does nothing | Implement search
W107 | Admin | Cleanliness Heatmap | My Location Button | Button | Cleanliness Heatmap/index.html | 178 | Center on GPS | No handler | None | No | DUMMY / PLACEHOLDER | Unwired icon button | Does nothing | Implement geolocation
W108 | Admin | Cleanliness Heatmap | Layers FAB | Button | Cleanliness Heatmap/index.html | 203 | Toggle map layers | No handler | None | No | DUMMY / PLACEHOLDER | Unwired button | Does nothing | Implement layers
W109 | Admin | Cleanliness Heatmap | Report FAB | Button | Cleanliness Heatmap/index.html | 206 | Create report | No handler | None | No | DUMMY / PLACEHOLDER | Unwired green action button | Does nothing | Implement action
W110 | Driver | Driver Dashboard | Profile Avatar Logout | Image | Driver Dashboard/index.html | 132 | Driver logout | Prompts confirm, clears localStorage | None | Yes (clears) | WORKING | Functional driver logout | None | None
W111 | Driver | Driver Dashboard | Notifications Bell | Button | Driver Dashboard/index.html | 138 | View notifications | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'You have no new notifications.' | Hardcoded | Implement notifications
W112 | Driver | Driver Dashboard | View Detailed Stats | Button | Driver Dashboard/index.html | 196 | View stats | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Loading detailed stats...' | No stats page | Implement stats
W113 | Driver | Driver Dashboard | Alert Acknowledge Buttons | Dynamic Buttons | driver.js:151 | Acknowledge alert | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Incident acknowledged' | No backend update | Implement acknowledge API
W114 | Driver | Driver Dashboard | Quick Task FAB | FAB | Driver Dashboard/index.html | 237 | Create quick task | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Opening quick task creation...' | No task form | Implement or remove
W115 | Driver | Driver Dashboard | GPS Telemetry Loop | Script | driver.js:22 | Track driver location | 5s interval getCurrentPosition + API call | POST /api/driver/update_location | Yes | WORKING | Real background GPS telemetry | None | None
W116 | Driver | Driver Dashboard | WebSocket Notifications | Script | driver.js:44 | Real-time push alerts | Connects to ws endpoint, triggers haptics | WS /api/ws/driver/{id} | No | WORKING | Real-time push connection | None | None
W117 | Driver | Driver Dashboard | Dashboard Data Loader | Script | driver.js:121 | Load dashboard stats | Fetches from API, updates DOM | GET /api/driver/dashboard | No (reads) | WORKING | Live server data | None | None
W118 | Driver | Driver Dashboard | Nav Home | Link | Driver Dashboard/index.html | 243 | Navigate home | driver.js nav router | None | No | WORKING | Routes to Driver Dashboard | None | None
W119 | Driver | Driver Dashboard | Nav Map | Link | Driver Dashboard/index.html | 247 | View map | driver.js nav router | None | No | WORKING | Routes to Navigation Screen | None | None
W120 | Driver | Driver Dashboard | Nav Tasks | Link | Driver Dashboard/index.html | 251 | View tasks | driver.js nav router | None | No | WORKING | Routes to Assigned Pickups | None | None
W121 | Driver | Driver Dashboard | Nav Reports | Link | Driver Dashboard/index.html | 255 | View reports | Toast: 'Feature coming soon!' | None | No | DUMMY / PLACEHOLDER | Placeholder toast | No reports page | Implement
W122 | Driver | Driver Dashboard | Nav Stats | Link | Driver Dashboard/index.html | 259 | View stats | Toast: 'Feature coming soon!' | None | No | DUMMY / PLACEHOLDER | Placeholder toast | No stats page | Implement
W123 | Driver | Assigned Pickups | Profile Avatar Logout | Image | Assigned Pickups/index.html | 138 | Driver logout | Prompts confirm | None | Yes (clears) | WORKING | Functional logout | None | None
W124 | Driver | Assigned Pickups | Notifications Bell | Button | Assigned Pickups/index.html | 143 | View notifications | No handler attached | None | No | BROKEN | Unwired button, click does nothing | Missing handler | Add handler
W125 | Driver | Assigned Pickups | Priority Filter | Button | Assigned Pickups/index.html | 172 | Filter by priority | No handler attached | None | No | BROKEN | Unwired filter button | No filter logic | Implement filter
W126 | Driver | Assigned Pickups | Task Details Buttons | Dynamic Buttons | driver.js:233 | View task details | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Viewing details for task X' | No detail modal | Implement detail view
W127 | Driver | Assigned Pickups | Start Route Buttons | Dynamic Buttons | driver.js:236 | Start navigation | Navigates to Navigation Screen with ID | None | No | WORKING | Real navigation with complaint_id | None | None
W128 | Driver | Assigned Pickups | Map Fullscreen Button | Button | Assigned Pickups/index.html | 194 | Fullscreen map | No handler | None | No | BROKEN | Unwired button | Does nothing | Implement or remove
W129 | Driver | Assigned Pickups | Static Task Card (Details) | Button | Assigned Pickups/index.html | 219 | View details | No handler (leftover template) | None | No | BROKEN | Dead static HTML | Leftover mock | Remove
W130 | Driver | Assigned Pickups | Static Task Card (Route) | Button | Assigned Pickups/index.html | 222 | Start route | No handler (leftover template) | None | No | BROKEN | Dead static HTML | Leftover mock | Remove
W131 | Driver | Assigned Pickups | Emergency FAB | FAB | Assigned Pickups/index.html | 232 | Emergency support | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Dispatching Emergency Support...' | No backend call | Implement or remove
W132 | Driver | Navigation Screen | Profile Avatar Logout | Image | Navigation Screen/index.html | 131 | Driver logout | Prompts confirm | None | Yes (clears) | WORKING | Functional logout | None | None
W133 | Driver | Navigation Screen | Notifications Bell | Button | Navigation Screen/index.html | 137 | View notifications | No handler | None | No | BROKEN | Unwired button | Does nothing | Add handler
W134 | Driver | Navigation Screen | Center Map FAB | Button | Navigation Screen/index.html | 207 | Center map | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Centering Map...' | No map pan | Implement
W135 | Driver | Navigation Screen | Map Layers FAB | Button | Navigation Screen/index.html | 210 | Toggle layers | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Toggling Map Layers...' | No layer toggle | Implement
W136 | Driver | Navigation Screen | Issue Button | Button | Navigation Screen/index.html | 195 | Report issue | Inline onclick toast | None | No | DUMMY / PLACEHOLDER | Toast: 'Opening issue reporter...' | No form | Implement
W137 | Driver | Navigation Screen | Arrived Button | Button | Navigation Screen/index.html | 199 | Confirm arrival | driver.js:253 reads ID, navigates | None | No | WORKING | Navigates to Pickup Verification | None | None
W138 | Driver | Pickup Verification | Profile Avatar Logout | Image | Pickup Verification/index.html | 140 | Driver logout | Prompts confirm | None | Yes (clears) | WORKING | Functional logout | None | None
W139 | Driver | Pickup Verification | Photo Capture Button | Button | Pickup Verification/index.html | 179 | Capture proof photo | Triggers file input click | None | No | WORKING | Opens camera/file picker | None | None
W140 | Driver | Pickup Verification | Waste Level Buttons (3) | Buttons | Pickup Verification/index.html | 216 | Select waste level | No handlers attached | None | No | BROKEN | Visual pills, not selectable, not submitted | Dead form controls | Wire toggle + submit
W141 | Driver | Pickup Verification | Report Issue Dropdown | Select | Pickup Verification/index.html | 240 | Report issue type | No id/name, never read by driver.js | None | No | DUMMY / PLACEHOLDER | Disconnected form control | User selection ignored | Add id and include
W142 | Driver | Pickup Verification | Confirm Pickup Button | Submit Button | Pickup Verification/index.html | 252 | Complete pickup | Form submit in driver.js:281 | POST /api/driver/complete_pickup | Yes | WORKING | Marks task COMPLETED and complaint RESOLVED | None | None
W143 | Driver | Pickup Verification | Notifications Bell | Button | Pickup Verification/index.html | 137 | View notifications | No handler | None | No | BROKEN | Unwired button | Does nothing | Add handler

## Feature Audit
Feature | Category | Status | Backend Endpoint | Frontend Implementation | Evidence | Notes
Authentication (Login) | Core | WORKING | POST /api/auth/login | auth.js + Login Screen form | JWT token, role-based redirect | Fully functional
Authentication (Registration) | Core | WORKING | POST /api/auth/register | auth.js + Register Screen form | Creates user as CITIZEN | Role selection ignored
Role-Based Access Control | Core | WORKING | Backend verify_citizen/driver/admin | auth.js redirectBasedOnRole | Backend enforces roles | Frontend role guard in citizen.js, driver.js, admin.js
Citizen Waste Reporting | Core | WORKING | POST /api/citizen/report_issue | citizen.js form handler | Persists complaint, awards +10 pts | Image upload orphaned
Complaint History | Core | PARTIALLY WORKING | GET /api/citizen/my_reports | citizen.js loadComplaints | Lists all reports with status | No detail drill-down on cards
Rewards & EcoPoints | Core | PARTIALLY WORKING | GET /api/citizen/rewards + POST redeem | citizen.js loadRewards + redeemReward | Points deducted, redemption logged | toast.js missing on Rewards page causes ReferenceError
Admin Dashboard Metrics | Core | WORKING | GET /api/admin/overview | admin.js loadAdminData | Total bins, critical bins, collection rate | Bin count uses formula (complaints * 12)
Admin Complaint Management | Core | WORKING | GET /api/admin/complaints | admin.js loadAdminComplaints | Lists all complaints with Assign button | No pagination
Admin Driver Assignment | Core | WORKING | POST /api/admin/assign_task | admin.js modal + confirm handler | Creates DriverTask, updates complaint, sends WebSocket | No duplicate-assignment check
Admin Driver Listing | Core | WORKING | GET /api/admin/drivers | admin.js driver select dropdown | Populates modal dropdown | No driver detail view
Driver Dashboard | Core | WORKING | GET /api/driver/dashboard | driver.js loadDriverDashboard | Shows task counts and greeting | completed_today counts all-time
Driver Task List | Core | WORKING | GET /api/driver/assigned_tasks | driver.js loadAssignedTasks | Shows assigned tasks with Start Route | Details button is toast-only
Driver Pickup Completion | Core | WORKING | POST /api/driver/complete_pickup | driver.js setupPickupVerification | Marks task COMPLETED, complaint RESOLVED | Waste level/issue dropdown ignored
Driver GPS Tracking | Core | WORKING | POST /api/driver/update_location | driver.js 5s interval | Real-time GPS upsert to database | No WebSocket broadcast to admin
WebSocket Notifications | Core | WORKING | WS /api/ws/driver/{id} | driver.js WebSocket handler | Real-time NEW_TASK push with haptics | Only driver-facing
Admin User Creation | Backend Only | PARTIALLY WORKING | POST /api/admin/create_user | No frontend UI | Endpoint works but no admin screen invokes it | Missing UI
Heatmap Visualization | UI | DUMMY / PLACEHOLDER | GET /api/admin/waste_heatmap | Static CSS markers in Waste Heatmap HTML | API returns coordinates but no map library renders them | Static visual representation
Illegal Dumping Detection | UI | PARTIALLY WORKING | GET /api/admin/illegal_dumping | admin.js loads stats but markers are static | Live stats from DB, markers are static HTML | AI prediction card is hardcoded
Cleanliness Heatmap | UI | DUMMY / PLACEHOLDER | None | Static HTML bin markers with CSS tooltips | Hardcoded bin locations and fill percentages | No real data integration
Map/Filter Controls | UI | DUMMY / PLACEHOLDER | None | Toast-only handlers in admin.js | By Ward, By Waste Type, District filter all show toasts | No actual filtering
Image Processing | Advertised | NOT IMPLEMENTED | None | File input exists but image discarded | Response says 'Image analysis queued' but nothing happens | Mentioned in API response only
AI/IoT Integration | Advertised | NOT IMPLEMENTED | None | None | No AI models, no IoT sensor feeds | Static mockup data only
Turn-by-Turn Navigation | UI | DUMMY / PLACEHOLDER | None | Navigation Screen shows static map image | No Google Maps or routing integration | Static visual
Automatic Dispatch | Advertised | NOT IMPLEMENTED | None | None | Admin manually assigns via modal | No algorithm
Search Functionality | UI | DUMMY / PLACEHOLDER | None | Cleanliness Heatmap search input unwired | Input exists but no handler | Implement search
Social/OAuth Login | UI | DUMMY / PLACEHOLDER | None | Google and Apple buttons on Login Screen | No OAuth handlers | Buttons are inert
Password Reset | UI | DUMMY / PLACEHOLDER | None | Forgot Password link is href='#' | No reset flow exists | Dead link
Onboarding Flow | UI | DUMMY / PLACEHOLDER | None | 3 screens exist but all buttons are unwired | Skip, Next, Get Started all inert | Wire navigation
Notification System | UI | DUMMY / PLACEHOLDER | None | Bell buttons exist on every screen | All show toast or are unwired | No notification backend
Role Selection Screen | UI | DUMMY / PLACEHOLDER | None | Role cards on Role Selection screen | No event handlers | Inert mockup screen

## Issues & Fixes
ID | Severity | Screen | Element | Status | Evidence | Recommended Fix
I001 | P0 | Citizen Dashboard | Bottom Nav Map | BROKEN | Navigates to Waste Heatmap which enforces Admin role guard | Create citizen-accessible map screen or add citizen role to Waste Heatmap auth
I002 | P0 | Citizen Dashboard | Bottom Nav Stats | BROKEN | Navigates to Cleanliness Heatmap which enforces Admin role guard | Same as above
I003 | P0 | Citizen Dashboard | Explore Nearby Bins | BROKEN | Same as I002 | Same fix needed
I004 | P0 | Rewards | Missing toast.js import | BROKEN | Rewards/index.html omits toast.js, causing ReferenceError on redeem | Add toast.js script tag to Rewards/index.html
I005 | P1 | Report Waste | Back Arrow Span | BROKEN | arrow_back is a span not button/a; citizen.js selector misses it | Wrap span in button element
I006 | P1 | Illegal Dumping | Dispatch Team Button | BROKEN | admin.js checks 'Dispatch Team' but button says 'Dispatching Team' | Fix string match or button text
I007 | P1 | Pickup Verification | Waste Level Buttons | BROKEN | 3 buttons (Empty/Partial/Full) have no handlers and are not submitted | Wire toggle handlers and include in form data
I008 | P1 | Pickup Verification | Report Issue Dropdown | DUMMY / PLACEHOLDER | Select has no id/name, never read by driver.js | Add id and include in complete_pickup payload
I009 | P1 | Report Waste | Image Upload | PARTIALLY WORKING | File picker works but image discarded on submit | Include file in FormData to backend
I010 | P1 | Assigned Pickups | Notifications Bell | BROKEN | No handler attached | Add click handler
I011 | P1 | Navigation Screen | Notifications Bell | BROKEN | No handler attached | Add click handler
I012 | P1 | Pickup Verification | Notifications Bell | BROKEN | No handler attached | Add click handler
I013 | P1 | Complaint History | Notifications Button | BROKEN | Lacks btn-notifications id | Add id and handler
I014 | P1 | Assigned Pickups | Priority Filter | BROKEN | No handler attached | Implement filter logic
I015 | P1 | Assigned Pickups | Static Mock Cards | BROKEN | Leftover static HTML template | Remove dead HTML
I016 | P1 | Assigned Pickups | Map Fullscreen | BROKEN | No handler | Implement or remove
I017 | P2 | Driver Dashboard | Alert Acknowledge | DUMMY / PLACEHOLDER | Toast only, no backend update | Implement acknowledge API endpoint
I018 | P2 | Report Waste | Description Textarea | DUMMY / PLACEHOLDER | No id/name, text discarded | Add id, include in submission
I019 | P2 | Report Waste | Refine GPS Button | DUMMY / PLACEHOLDER | No handler | Implement geolocation refresh
I020 | P2 | All Screens | Notification Bells | DUMMY / PLACEHOLDER | All show hardcoded toast or are unwired | Implement notification system
I021 | P2 | Login Screen | Password Visibility | DUMMY / PLACEHOLDER | No toggle handler | Implement password toggle
I022 | P2 | Login Screen | Remember Me | DUMMY / PLACEHOLDER | Not read by auth.js | Implement or remove
I023 | P2 | Login Screen | Forgot Password | DUMMY / PLACEHOLDER | Dead href='#' link | Implement reset flow or remove
I024 | P2 | Login Screen | Social Login Buttons | DUMMY / PLACEHOLDER | No OAuth handlers | Remove or implement
I025 | P3 | Onboarding 1-3 | All Buttons | DUMMY / PLACEHOLDER | Skip, Next, Get Started all inert | Wire navigation between screens
I026 | P3 | Role Selection | All Cards | DUMMY / PLACEHOLDER | No click handlers | Wire navigation or remove screen
I027 | P3 | Rewards | Tier Progress / Leaderboard | DUMMY / PLACEHOLDER | All static hardcoded data | Implement dynamic data
I028 | P3 | Admin Screens | All Map Markers | DUMMY / PLACEHOLDER | Static HTML, no map library | Integrate real map library
I029 | P3 | Admin Screens | Filter Controls | DUMMY / PLACEHOLDER | All toast-only | Implement actual filtering